## login-page
Test Case Project |  | Website to Rate Professors | Test Case Description | Login functionality test — verifying valid/invalid login, forgot password, and support mail redirection.
Created By |  | M. Ashritha | Reviewed By | V. Anjusree Reddy | Version |  | 1.0
QA Tester’s Log |  | Review comments in version 1.0
Tester's Name |  | M. Ashritha | Date Tested | 2025-05-05 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify on entering valid userid and password, the customer can login . Entering Forgot password on popup and send mail to consultant
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Navigate to http://127.0.0.1:5500/index.html |  | Site should open | As Expected |  | Pass
2 | Enter Valid Userid & Password |  | Fields accept input | As Expected |  | Pass
3 | Click Login button |  | User should be logged in | As Expected |  | Pass
Dialogue box for forgot password
4 | Click on Forgot Password |  | Popup will appear with form | As Expected |  | Pass
5 | Enter registered email |  | Field accepts email | As Expected |  | Pass
6 | Click on Reset button |  | An email sent to Consultant mail id | Not getting Recovery password as Expected |  | Fail

## Active Cases
Test Case Project |  | Website to rate professors |  | Test Case Description |  | Test the functionality of viewing, filtering, and comparing rating cases.
Created By |  | M. Ashritha | Reviewed By |  | V. Anjusree Reddy |  | Version |  | 1.0
QA Tester’s Log
Tester's Name |  | M. Ashritha | Date Tested |  | 2025-05-05 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario
Step # | Step Details |  | Expected Results |  | Actual Results |  |  | Pass / Fail / Not executed / Suspended
Search Page
1 | Shift betweent the options of searching by professor or university |  | Search bar adjusts accordingly |  | As expected |  |  | Pass
2 | Click on the search bar |  | Search bar activates and allows text input |  | As expected |  |  | Pass
3 | search for any professor or university by typing the name |  | Redirects to university/professor page |  | Search bar does not display matching universities unless the full name is typed |  |  | Partially fail
4 | Type gibberish like "abcxyz" and press enter |  | Shows message like "No results found" or does not redirect |  | Doesn't show the “No results” message properly |  |  | Fail
Professor Profile Page
5 | Open Professor Profile Page |  | Page loads with professor list and details like rating, reviews, department shown |  | As expected |  |  | Pass
6 | Submit review with all fields correctly filled |  | Review added and reflected without error |  | As expected |  |  | Pass
7 | Leave "Rating" field empty and submit |  | Validation error shown ( "Please fill out this field") |  | As expected |  |  | Pass
8 | Go to compare page |  | Side-by-side comparison is displayed |  | As expected |  |  | Pass
9 | Select the professors using search bar |  | Side-by-side comparison is displayed with selected university |  | Search bar does not display matching universities unless the full name is typed |  |  | Partially fail
University Page
10 | Open University Profile Page |  | Page loads with university list and details like rating, reviews are shown |  | As expected |  |  | Pass
11
12 | Submit review with all fields correctly filled |  | Review added and reflected without error |  | As expected |  |  | Pass
13 | Leave "Rating" field empty and submit |  | Validation error shown ( "Please fill out this field") |  | As expected |  |  | Pass
14 | Go to compare page |  | Side-by-side comparison is displayed |  | As expected |  |  | Pass
15 | Select the university using search bar |  | Side-by-side comparison is displayed with selected univerity |  | Search bar does not display matching universities unless the full name is typed |  |  | Partially fail

## admin-Manage User
Test Case Project |  | Website to rate professors | Test Case Description | Verify that the admin can add, edit, and manage users with proper validations.
Created By |  | M. Ashritha | Reviewed By | V. Anjusree Reddy | Version |  | 1.0
QA Tester’s Log |  | Review comments in version 1.0
Tester's Name |  | M. Ashritha | Date Tested | 2025-05-05 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Add User
1 | Click on "Add User" button |  | Opens a form with fields: Name, Email, Role, Password, etc. | As expected |  | Pass
2 | Fill all valid details and click "Submit" |  | User gets added to the user list with confirmation message | UI Validation Message Not Displayed |  | Fail
3 | Submit with an already existing user ID |  | System shows error "User already exists" | As expected |  | Pass
4 | Leave required field blank and click "Submit" |  | System shows validation errors for required fields | Validation messages appear |  | Pass
Edit User
5 | Click "Edit" button next to a user |  | Pre-filled form opens with current user data | As expected |  | Pass
6 | Change the role and click "Update" |  | Role gets updated with confirmation message | Role updated successfully |  | Pass
7 | Delete user |  | Deletes the user | As expected |  | Pass
8 | Submit with invalid data (e.g., blank name) |  | Validation error message shown | As expected |  | Pass

## logout
Test Case Project |  | Website to rate professors | Test Case Description | Verify that the user is securely logged out and redirected to the login page
Created By |  | M. Ashritha | Reviewed By | V. Anjusree Reddy | Version |  | 1.0
QA Tester’s Log |  | Review comments in version 1.0
Tester's Name |  | M. Ashritha | Date Tested | 2025-05-05 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
1 | Click on the "logout" button in the navigation bar |  | User is logged out and redirected to login page | Redirected to login page |  | Pass